## Summary
total_stages | delayed_stages | early_stages | on_time_stages | pending_stages | pending_overdue_stages | total_delay_days | average_delay_days | critical_path_delays | po_id
31 | 3 | 8 | 2 | 10 | 5 | 87 | 29 | 6 | PO373283MOUN-0000071
31 | 3 | 0 | 0 | 0 | 6 | 196 | 65.33 | 6 | PO373323PXIN-0001031
31 | 3 | 1 | 2 | 0 | 3 | 70 | 23.33 | 4 | PO373366ROOM-0337551
31 | 1 | 0 | 0 | 0 | 8 | 100 | 100 | 6 | PO373771AMAZ-0002481
31 | 3 | 1 | 0 | 0 | 21 | 1794 | 598 | 19 | PO373857M2B3-10030650

## Stage Delays
stage_id | stage_name | target_timestamp | actual_timestamp | delay_days | delay_status | delay_reason | team_responsible | po_id
1 | 01. PO Approval Pending | 2025-05-12T00:00:00 | 2025-05-13T00:00:00 | 1 | delayed | Actual completion 1 days after target | Procurement | PO373283MOUN-0000071
2 | 02. Supplier Confirmation Pending | 2025-05-16T00:00:00 | 2025-05-21T00:00:00 | 5 | delayed | Actual completion 5 days after target | Procurement | PO373283MOUN-0000071
3 | 03. PI Upload Pending | 2025-05-22T00:00:00 | 2025-05-26T00:00:00 | 4 | delayed | Actual completion 4 days after target | Procurement | PO373283MOUN-0000071
4 | 04. PI Approval Pending | 2025-05-28T00:00:00 | 2025-05-26T00:00:00 | -2 | early | Completed 2 days before target | Finance | PO373283MOUN-0000071
5 | 05. PI Payment Pending | 2025-05-31T00:00:00 | 2025-05-29T00:00:00 | -2 | early | Completed 2 days before target | Finance | PO373283MOUN-0000071
6 | 06. Packaging Pending | 2025-06-01T00:00:00 |  | 25 | pending_overdue | Stage incomplete, 25 days overdue | Operations | PO373283MOUN-0000071
7 | 07. Transparency Label Pending | 2025-05-31T00:00:00 |  | 26 | pending_overdue | Stage incomplete, 26 days overdue | Operations | PO373283MOUN-0000071
8 | 08. PRD Pending | 2025-05-31T00:00:00 | 2025-05-23T00:00:00 | -8 | early | Completed 8 days before target | Finance | PO373283MOUN-0000071
9 | 09. Under Production | 2025-06-07T00:00:00 |  | 19 | pending_overdue | Stage incomplete, 19 days overdue | Supplier | PO373283MOUN-0000071
10 | 10. PRD Confirmation Pending |  | 2025-06-13T00:00:00 |  | unknown |  |  | PO373283MOUN-0000071
11 | 11. IM Sign-Off Pending | 2025-06-16T00:00:00 | 2025-06-16T00:00:00 | 0 | on_time | Completed on target date | Operations | PO373283MOUN-0000071
12 | 12. Ready for Batching Pending | 2025-06-17T00:00:00 | 2025-06-17T00:00:00 | 0 | on_time | Completed on target date | Operations | PO373283MOUN-0000071
13 | 13. Batch Creation Pending | 2025-06-18T00:00:00 | 2025-06-17T11:00:00 | -1 | early | Completed 1 days before target | Operations | PO373283MOUN-0000071
14 | 14. SM Sign-Off Pending | 2025-06-19T11:00:00 | 2025-06-18T09:46:00 | -2 | early | Completed 2 days before target | Operations | PO373283MOUN-0000071
15 | 15. CI Approval Pending |  |  |  | unknown |  |  | PO373283MOUN-0000071
16 | 16. CI Payment Pending |  |  |  | unknown |  |  | PO373283MOUN-0000071
17 | 17. QC Schedule Pending | 2025-06-20T09:46:00 |  | 6 | pending_overdue | Stage incomplete, 6 days overdue | Quality | PO373283MOUN-0000071
18 | 18. FFW Booking Missing | 2025-06-21T09:46:00 | 2025-06-18T12:38:00 | -3 | early | Completed 3 days before target | Logistics | PO373283MOUN-0000071
19 | 19. Supplier Pickup Date Pending | 2025-06-24T09:46:00 | 2025-06-20T05:30:00 | -5 | early | Completed 5 days before target | Logistics | PO373283MOUN-0000071
20 | 20. Pre Pickup Check | 2025-06-25T09:46:00 |  | 1 | pending_overdue | Stage incomplete, 1 days overdue | Quality | PO373283MOUN-0000071
21 | 21. FOB Pickup Pending | 2025-06-27T09:46:00 |  |  | pending | Stage not yet completed |  | PO373283MOUN-0000071
22 | 22. Non FOB Pickup Pending | 2025-06-27T09:46:00 |  |  | pending | Stage not yet completed |  | PO373283MOUN-0000071
23 | 23. INB Creation Pending | 2025-06-28T09:46:00 |  |  | pending | Stage not yet completed |  | PO373283MOUN-0000071
24 | 24. Mark In-Transit Pending | 2025-07-01T09:46:00 |  |  | pending | Stage not yet completed |  | PO373283MOUN-0000071
25 | 25. BL Approval Pending | 2025-07-02T09:46:00 | 2025-06-20T00:00:00 | -13 | early | Completed 13 days before target | Finance | PO373283MOUN-0000071
26 | 26. BL Payment Pending - In Transit | 2025-07-07T09:46:00 |  |  | pending | Stage not yet completed |  | PO373283MOUN-0000071
27 | 27. BL Payment Pending - Arrived | 2025-07-05T09:46:00 |  |  | pending | Stage not yet completed |  | PO373283MOUN-0000071
28 | 28. Telex Release Pending | 2025-07-08T09:46:00 |  |  | pending | Stage not yet completed |  | PO373283MOUN-0000071
29 | 29. Stock Delivery Pending | 2025-07-10T09:46:00 |  |  | pending | Stage not yet completed |  | PO373283MOUN-0000071
30 | 30. Stock Receiving Pending | 2025-07-11T09:46:00 |  |  | pending | Stage not yet completed |  | PO373283MOUN-0000071
31 | 31. Dispute - PO Closing Pending | 2025-07-13T09:46:00 |  |  | pending | Stage not yet completed |  | PO373283MOUN-0000071
1 | 01. PO Approval Pending | 2025-05-12T00:00:00 | 2025-05-13T00:00:00 | 1 | delayed | Actual completion 1 days after target | Procurement | PO373323PXIN-0001031
2 | 02. Supplier Confirmation Pending | 2025-05-16T00:00:00 | 2025-05-21T00:00:00 | 5 | delayed | Actual completion 5 days after target | Procurement | PO373323PXIN-0001031
3 | 03. PI Upload Pending | 2025-05-22T00:00:00 |  | 35 | pending_overdue | Stage incomplete, 35 days overdue | Procurement | PO373323PXIN-0001031
4 | 04. PI Approval Pending | 2025-05-24T00:00:00 |  | 33 | pending_overdue | Stage incomplete, 33 days overdue | Finance | PO373323PXIN-0001031
5 | 05. PI Payment Pending | 2025-05-29T00:00:00 |  | 28 | pending_overdue | Stage incomplete, 28 days overdue | Finance | PO373323PXIN-0001031
6 | 06. Packaging Pending | 2025-05-24T00:00:00 |  | 33 | pending_overdue | Stage incomplete, 33 days overdue | Operations | PO373323PXIN-0001031
7 | 07. Transparency Label Pending | 2025-05-23T00:00:00 |  | 34 | pending_overdue | Stage incomplete, 34 days overdue | Operations | PO373323PXIN-0001031
8 | 08. PRD Pending | 2025-05-23T00:00:00 | 2025-05-26T00:00:00 | 3 | delayed | Actual completion 3 days after target | Finance | PO373323PXIN-0001031
9 | 09. Under Production | 2025-06-02T00:00:00 |  | 24 | pending_overdue | Stage incomplete, 24 days overdue | Supplier | PO373323PXIN-0001031
10 | 10. PRD Confirmation Pending |  |  |  | unknown |  |  | PO373323PXIN-0001031
11 | 11. IM Sign-Off Pending |  |  |  | unknown |  |  | PO373323PXIN-0001031
12 | 12. Ready for Batching Pending |  |  |  | unknown |  |  | PO373323PXIN-0001031
13 | 13. Batch Creation Pending |  |  |  | unknown |  |  | PO373323PXIN-0001031
14 | 14. SM Sign-Off Pending |  |  |  | unknown |  |  | PO373323PXIN-0001031
15 | 15. CI Approval Pending |  |  |  | unknown |  |  | PO373323PXIN-0001031
16 | 16. CI Payment Pending |  |  |  | unknown |  |  | PO373323PXIN-0001031
17 | 17. QC Schedule Pending |  |  |  | unknown |  |  | PO373323PXIN-0001031
18 | 18. FFW Booking Missing |  |  |  | unknown |  |  | PO373323PXIN-0001031
19 | 19. Supplier Pickup Date Pending |  |  |  | unknown |  |  | PO373323PXIN-0001031
20 | 20. Pre Pickup Check |  |  |  | unknown |  |  | PO373323PXIN-0001031
21 | 21. FOB Pickup Pending |  |  |  | unknown |  |  | PO373323PXIN-0001031
22 | 22. Non FOB Pickup Pending |  |  |  | unknown |  |  | PO373323PXIN-0001031
23 | 23. INB Creation Pending |  |  |  | unknown |  |  | PO373323PXIN-0001031
24 | 24. Mark In-Transit Pending |  |  |  | unknown |  |  | PO373323PXIN-0001031
25 | 25. BL Approval Pending |  |  |  | unknown |  |  | PO373323PXIN-0001031
26 | 26. BL Payment Pending - In Transit |  |  |  | unknown |  |  | PO373323PXIN-0001031
27 | 27. BL Payment Pending - Arrived |  |  |  | unknown |  |  | PO373323PXIN-0001031
28 | 28. Telex Release Pending |  |  |  | unknown |  |  | PO373323PXIN-0001031
29 | 29. Stock Delivery Pending |  |  |  | unknown |  |  | PO373323PXIN-0001031
30 | 30. Stock Receiving Pending |  |  |  | unknown |  |  | PO373323PXIN-0001031
31 | 31. Dispute - PO Closing Pending |  |  |  | unknown |  |  | PO373323PXIN-0001031
1 | 01. PO Approval Pending | 2025-05-12T00:00:00 | 2025-05-13T00:00:00 | 1 | delayed | Actual completion 1 days after target | Procurement | PO373366ROOM-0337551
2 | 02. Supplier Confirmation Pending | 2025-05-16T00:00:00 | 2025-05-26T00:00:00 | 10 | delayed | Actual completion 10 days after target | Procurement | PO373366ROOM-0337551
3 | 03. PI Upload Pending | 2025-05-27T00:00:00 | 2025-05-27T00:00:00 | 0 | on_time | Completed on target date | Procurement | PO373366ROOM-0337551
4 | 04. PI Approval Pending | 2025-05-29T00:00:00 | 2025-05-27T00:00:00 | -2 | early | Completed 2 days before target | Finance | PO373366ROOM-0337551
5 | 05. PI Payment Pending | 2025-06-01T00:00:00 | 2025-06-02T00:00:00 | 1 | delayed | Actual completion 1 days after target | Finance | PO373366ROOM-0337551
6 | 06. Packaging Pending | 2025-06-05T00:00:00 |  | 21 | pending_overdue | Stage incomplete, 21 days overdue | Operations | PO373366ROOM-0337551
7 | 07. Transparency Label Pending | 2025-06-04T00:00:00 |  | 22 | pending_overdue | Stage incomplete, 22 days overdue | Operations | PO373366ROOM-0337551
8 | 08. PRD Pending | 2025-06-04T00:00:00 | 2025-06-04T00:00:00 | 0 | on_time | Completed on target date | Finance | PO373366ROOM-0337551
9 | 09. Under Production | 2025-06-11T00:00:00 |  | 15 | pending_overdue | Stage incomplete, 15 days overdue | Supplier | PO373366ROOM-0337551
10 | 10. PRD Confirmation Pending |  |  |  | unknown |  |  | PO373366ROOM-0337551
11 | 11. IM Sign-Off Pending |  |  |  | unknown |  |  | PO373366ROOM-0337551
12 | 12. Ready for Batching Pending |  |  |  | unknown |  |  | PO373366ROOM-0337551
13 | 13. Batch Creation Pending |  |  |  | unknown |  |  | PO373366ROOM-0337551
14 | 14. SM Sign-Off Pending |  |  |  | unknown |  |  | PO373366ROOM-0337551
15 | 15. CI Approval Pending |  |  |  | unknown |  |  | PO373366ROOM-0337551
16 | 16. CI Payment Pending |  |  |  | unknown |  |  | PO373366ROOM-0337551
17 | 17. QC Schedule Pending |  |  |  | unknown |  |  | PO373366ROOM-0337551
18 | 18. FFW Booking Missing |  |  |  | unknown |  |  | PO373366ROOM-0337551
19 | 19. Supplier Pickup Date Pending |  |  |  | unknown |  |  | PO373366ROOM-0337551
20 | 20. Pre Pickup Check |  |  |  | unknown |  |  | PO373366ROOM-0337551
21 | 21. FOB Pickup Pending |  |  |  | unknown |  |  | PO373366ROOM-0337551
22 | 22. Non FOB Pickup Pending |  |  |  | unknown |  |  | PO373366ROOM-0337551
23 | 23. INB Creation Pending |  |  |  | unknown |  |  | PO373366ROOM-0337551
24 | 24. Mark In-Transit Pending |  |  |  | unknown |  |  | PO373366ROOM-0337551
25 | 25. BL Approval Pending |  |  |  | unknown |  |  | PO373366ROOM-0337551
26 | 26. BL Payment Pending - In Transit |  |  |  | unknown |  |  | PO373366ROOM-0337551
27 | 27. BL Payment Pending - Arrived |  |  |  | unknown |  |  | PO373366ROOM-0337551
28 | 28. Telex Release Pending |  |  |  | unknown |  |  | PO373366ROOM-0337551
29 | 29. Stock Delivery Pending |  |  |  | unknown |  |  | PO373366ROOM-0337551
30 | 30. Stock Receiving Pending |  |  |  | unknown |  |  | PO373366ROOM-0337551
31 | 31. Dispute - PO Closing Pending |  |  |  | unknown |  |  | PO373366ROOM-0337551
1 | 01. PO Approval Pending | 2025-05-27T00:00:00 | 2025-06-04T00:00:00 | 8 | delayed | Actual completion 8 days after target | Procurement | PO373771AMAZ-0002481
2 | 02. Supplier Confirmation Pending | 2025-06-07T00:00:00 |  | 19 | pending_overdue | Stage incomplete, 19 days overdue | Procurement | PO373771AMAZ-0002481
3 | 03. PI Upload Pending | 2025-06-08T00:00:00 |  | 18 | pending_overdue | Stage incomplete, 18 days overdue | Procurement | PO373771AMAZ-0002481
4 | 04. PI Approval Pending | 2025-06-10T00:00:00 |  | 16 | pending_overdue | Stage incomplete, 16 days overdue | Finance | PO373771AMAZ-0002481
5 | 05. PI Payment Pending | 2025-06-15T00:00:00 |  | 11 | pending_overdue | Stage incomplete, 11 days overdue | Finance | PO373771AMAZ-0002481
6 | 06. Packaging Pending | 2025-06-18T00:00:00 |  | 8 | pending_overdue | Stage incomplete, 8 days overdue | Operations | PO373771AMAZ-0002481
7 | 07. Transparency Label Pending | 2025-06-17T00:00:00 |  | 9 | pending_overdue | Stage incomplete, 9 days overdue | Operations | PO373771AMAZ-0002481
8 | 08. PRD Pending | 2025-06-17T00:00:00 |  | 9 | pending_overdue | Stage incomplete, 9 days overdue | Finance | PO373771AMAZ-0002481
9 | 09. Under Production | 2025-06-24T00:00:00 |  | 2 | pending_overdue | Stage incomplete, 2 days overdue | Supplier | PO373771AMAZ-0002481
10 | 10. PRD Confirmation Pending |  |  |  | unknown |  |  | PO373771AMAZ-0002481
11 | 11. IM Sign-Off Pending |  |  |  | unknown |  |  | PO373771AMAZ-0002481
12 | 12. Ready for Batching Pending |  |  |  | unknown |  |  | PO373771AMAZ-0002481
13 | 13. Batch Creation Pending |  |  |  | unknown |  |  | PO373771AMAZ-0002481
14 | 14. SM Sign-Off Pending |  |  |  | unknown |  |  | PO373771AMAZ-0002481
15 | 15. CI Approval Pending |  |  |  | unknown |  |  | PO373771AMAZ-0002481
16 | 16. CI Payment Pending |  |  |  | unknown |  |  | PO373771AMAZ-0002481
17 | 17. QC Schedule Pending |  |  |  | unknown |  |  | PO373771AMAZ-0002481
18 | 18. FFW Booking Missing |  |  |  | unknown |  |  | PO373771AMAZ-0002481
19 | 19. Supplier Pickup Date Pending |  |  |  | unknown |  |  | PO373771AMAZ-0002481
20 | 20. Pre Pickup Check |  |  |  | unknown |  |  | PO373771AMAZ-0002481
21 | 21. FOB Pickup Pending |  |  |  | unknown |  |  | PO373771AMAZ-0002481
22 | 22. Non FOB Pickup Pending |  |  |  | unknown |  |  | PO373771AMAZ-0002481
23 | 23. INB Creation Pending |  |  |  | unknown |  |  | PO373771AMAZ-0002481
24 | 24. Mark In-Transit Pending |  |  |  | unknown |  |  | PO373771AMAZ-0002481
25 | 25. BL Approval Pending |  |  |  | unknown |  |  | PO373771AMAZ-0002481
26 | 26. BL Payment Pending - In Transit |  |  |  | unknown |  |  | PO373771AMAZ-0002481
27 | 27. BL Payment Pending - Arrived |  |  |  | unknown |  |  | PO373771AMAZ-0002481
28 | 28. Telex Release Pending |  |  |  | unknown |  |  | PO373771AMAZ-0002481
29 | 29. Stock Delivery Pending |  |  |  | unknown |  |  | PO373771AMAZ-0002481
30 | 30. Stock Receiving Pending |  |  |  | unknown |  |  | PO373771AMAZ-0002481
31 | 31. Dispute - PO Closing Pending |  |  |  | unknown |  |  | PO373771AMAZ-0002481
1 | 01. PO Approval Pending | 2025-05-28T00:00:00 | 2025-06-04T00:00:00 | 7 | delayed | Actual completion 7 days after target | Procurement | PO373857M2B3-10030650
2 | 02. Supplier Confirmation Pending | 2025-06-07T00:00:00 |  | 19 | pending_overdue | Stage incomplete, 19 days overdue | Procurement | PO373857M2B3-10030650
3 | 03. PI Upload Pending | 2025-06-08T00:00:00 |  | 18 | pending_overdue | Stage incomplete, 18 days overdue | Procurement | PO373857M2B3-10030650
4 | 04. PI Approval Pending | 2025-06-10T00:00:00 |  | 16 | pending_overdue | Stage incomplete, 16 days overdue | Finance | PO373857M2B3-10030650
5 | 05. PI Payment Pending | 2025-06-15T00:00:00 |  | 11 | pending_overdue | Stage incomplete, 11 days overdue | Finance | PO373857M2B3-10030650
6 | 06. Packaging Pending | 2025-06-18T00:00:00 |  | 8 | pending_overdue | Stage incomplete, 8 days overdue | Operations | PO373857M2B3-10030650
7 | 07. Transparency Label Pending | 2025-06-17T00:00:00 |  | 9 | pending_overdue | Stage incomplete, 9 days overdue | Operations | PO373857M2B3-10030650
8 | 08. PRD Pending | 2025-06-17T00:00:00 |  | 9 | pending_overdue | Stage incomplete, 9 days overdue | Finance | PO373857M2B3-10030650
9 | 09. Under Production | 2025-06-24T00:00:00 |  | 2 | pending_overdue | Stage incomplete, 2 days overdue | Supplier | PO373857M2B3-10030650
10 | 10. PRD Confirmation Pending |  |  |  | unknown |  |  | PO373857M2B3-10030650
11 | 11. IM Sign-Off Pending |  |  |  | unknown |  |  | PO373857M2B3-10030650
12 | 12. Ready for Batching Pending |  |  |  | unknown |  |  | PO373857M2B3-10030650
13 | 13. Batch Creation Pending |  | 2024-06-28T12:35:00 |  | unknown |  |  | PO373857M2B3-10030650
14 | 14. SM Sign-Off Pending | 2024-06-28T12:35:00 | 2025-01-28T06:26:00 | 213 | delayed | Actual completion 213 days after target | Operations | PO373857M2B3-10030650
15 | 15. CI Approval Pending |  |  |  | unknown |  |  | PO373857M2B3-10030650
16 | 16. CI Payment Pending |  |  |  | unknown |  |  | PO373857M2B3-10030650
17 | 17. QC Schedule Pending | 2025-01-30T06:26:00 |  | 147 | pending_overdue | Stage incomplete, 147 days overdue | Quality | PO373857M2B3-10030650
18 | 18. FFW Booking Missing | 2025-01-31T06:26:00 | 2024-11-18T16:06:00 | -74 | early | Completed 74 days before target | Logistics | PO373857M2B3-10030650
19 | 19. Supplier Pickup Date Pending | 2025-02-03T06:26:00 | 2025-02-26T18:20:00 | 23 | delayed | Actual completion 23 days after target | Logistics | PO373857M2B3-10030650
20 | 20. Pre Pickup Check | 2025-02-27T18:20:00 |  | 118 | pending_overdue | Stage incomplete, 118 days overdue | Quality | PO373857M2B3-10030650
21 | 21. FOB Pickup Pending | 2025-03-01T18:20:00 |  | 116 | pending_overdue | Stage incomplete, 116 days overdue | Logistics | PO373857M2B3-10030650
22 | 22. Non FOB Pickup Pending | 2025-03-01T18:20:00 |  | 116 | pending_overdue | Stage incomplete, 116 days overdue | Logistics | PO373857M2B3-10030650
23 | 23. INB Creation Pending | 2025-03-02T18:20:00 |  | 115 | pending_overdue | Stage incomplete, 115 days overdue | Logistics | PO373857M2B3-10030650
24 | 24. Mark In-Transit Pending | 2025-03-05T18:20:00 |  | 112 | pending_overdue | Stage incomplete, 112 days overdue | Logistics | PO373857M2B3-10030650
25 | 25. BL Approval Pending | 2025-03-06T18:20:00 |  | 111 | pending_overdue | Stage incomplete, 111 days overdue | Finance | PO373857M2B3-10030650
26 | 26. BL Payment Pending - In Transit | 2025-03-11T18:20:00 |  | 106 | pending_overdue | Stage incomplete, 106 days overdue | Finance | PO373857M2B3-10030650
27 | 27. BL Payment Pending - Arrived | 2025-03-09T18:20:00 |  | 108 | pending_overdue | Stage incomplete, 108 days overdue | Finance | PO373857M2B3-10030650
28 | 28. Telex Release Pending | 2025-03-12T18:20:00 |  | 105 | pending_overdue | Stage incomplete, 105 days overdue | Finance | PO373857M2B3-10030650
29 | 29. Stock Delivery Pending | 2025-03-14T18:20:00 |  | 103 | pending_overdue | Stage incomplete, 103 days overdue | Logistics | PO373857M2B3-10030650
30 | 30. Stock Receiving Pending | 2025-03-15T18:20:00 |  | 102 | pending_overdue | Stage incomplete, 102 days overdue | Warehouse | PO373857M2B3-10030650
31 | 31. Dispute - PO Closing Pending | 2025-03-17T18:20:00 |  | 100 | pending_overdue | Stage incomplete, 100 days overdue | Finance | PO373857M2B3-10030650

## Team Performance
total_stages | delayed_stages | total_delay_days | average_delay_days | team | po_id
3 | 3 | 10 | 3.33 | Procurement | PO373283MOUN-0000071
4 | 0 | 0 | 0 | Finance | PO373283MOUN-0000071
6 | 2 | 51 | 25.5 | Operations | PO373283MOUN-0000071
1 | 1 | 19 | 19 | Supplier | PO373283MOUN-0000071
2 | 2 | 7 | 3.5 | Quality | PO373283MOUN-0000071
2 | 0 | 0 | 0 | Logistics | PO373283MOUN-0000071
3 | 3 | 41 | 13.67 | Procurement | PO373323PXIN-0001031
3 | 3 | 64 | 21.33 | Finance | PO373323PXIN-0001031
2 | 2 | 67 | 33.5 | Operations | PO373323PXIN-0001031
1 | 1 | 24 | 24 | Supplier | PO373323PXIN-0001031
3 | 2 | 11 | 5.5 | Procurement | PO373366ROOM-0337551
3 | 1 | 1 | 1 | Finance | PO373366ROOM-0337551
2 | 2 | 43 | 21.5 | Operations | PO373366ROOM-0337551
1 | 1 | 15 | 15 | Supplier | PO373366ROOM-0337551
3 | 3 | 45 | 15 | Procurement | PO373771AMAZ-0002481
3 | 3 | 36 | 12 | Finance | PO373771AMAZ-0002481
2 | 2 | 17 | 8.5 | Operations | PO373771AMAZ-0002481
1 | 1 | 2 | 2 | Supplier | PO373771AMAZ-0002481
3 | 3 | 44 | 14.67 | Procurement | PO373857M2B3-10030650
8 | 8 | 566 | 70.75 | Finance | PO373857M2B3-10030650
3 | 3 | 230 | 76.67 | Operations | PO373857M2B3-10030650
1 | 1 | 2 | 2 | Supplier | PO373857M2B3-10030650
2 | 2 | 265 | 132.5 | Quality | PO373857M2B3-10030650
7 | 6 | 585 | 97.5 | Logistics | PO373857M2B3-10030650
1 | 1 | 102 | 102 | Warehouse | PO373857M2B3-10030650