## DoD
po_razin_id | po_created_date | po_approval_date | supplier_confirmation_date | pi_invoice_approval_date | pi_payment_date | receive_first_prd_date | prd_reconfirmed_date | po_im_date_value | po_sm_date_value | batch_created_ts | sm_signoff_ts | ci_invoice_approval_date | ci_payment_date | qc_schedule_date | ffw_booking_ts | spd_ts | stock_pickup_date | shipment_creation_date | shipment_in_transit_date | bi_invoice_approval_date | bi_payment_date | ffwp_telex_release_date | shipment_stock_delivery_date | item_receipt_date | actual_cargo_pick_up_date | actual_shipping_date | actual_arrival_date | actual_delivery_date | first_prd_date | final_prd_date | planned_prd | batch_spd | qi_date | ETA | PLT | Status | Days | A. Anti PO Line | B. Compliance Blocked | C. Shipped | D. Master Data Blocker | 01. PO Approval Pending | 02. Supplier Confirmation Pending | 03. PI Upload Pending | 04. PI Approval Pending | 05. PI Payment Pending | 06. Packaging Pending | 07. Transperancy Label Pending | 08. PRD Pending | 09. Under Production | 10. PRD Confirmation Pending | 11. IM Sign-Off Pending | 12. Ready for Batching Pending | 13. Batch Creation Pending | 14. SM Sign-Off Pending | 15. CI Approval Pending | 16. CI Payment Pending | 17. QC Schedule Pending | 18. FFW Booking Missing | 19. Supplier Pickup Date Pending | 20. Pre Pickup Check | 21. FOB Pickup Pending | 22. Non FOB Pickup Pending | 23. INB Creation Pending | 24. Mark In-Transit Pending | 25. BL Approval Pending | 26. BL Payment Pending - In Transit | 27. BL Payment Pending - Arrived | 28. Telex Release Pending | 29. Stock Delivery Pending | 30. Stock Receiving Pending | 31. Dispute - PO Closing Pending | pi_applicable | ci_applicable
PO374147PROB-0001921 | 2025-06-02 | 2025-06-03 | 2025-06-04 |  |  | 2025-06-05 | 2025-06-09 | 2025-06-12 |  | 2025-06-13 09:47 | [18 empty] | 2025-07-03 | 2025-07-03 | 2025-09-30 |  |  |  | 105 | 14. SM Sign-Off Pending | 4 | [17 empty] | 4 | [17 empty] | 1 | 0